## Report Info
SauceDemo Manual Test Defect Report
Field | Value | Note
Application under test | SauceDemo (Swag Labs)
URL | https://www.saucedemo.com
Tester | Haleem
Test type | Manual, exploratory
Date tested | 18th April, 2026
Browser and version | Chrome 155.0.8059
Operating system | Windows
Accounts tested | problem_user, error_user
Severity legend (technical impact)
Level | Definition | Example from this report
Critical | Blocks a core flow (browse → cart → checkout) with no workaround. | DEF-005: half the catalog cannot be added to cart
High | Major feature broken or wrong data shown; workaround is difficult. | DEF-004: sorting is broken
Medium | Feature partly impaired, or a workaround exists. | DEF-009: Remove works only from the Cart page
Low | Cosmetic or minor; no flow is affected. | DEF-008: Reset App State not clickable
Priority legend (business urgency)
Level | Definition
Urgency | Fix Immediately, requiring rapid attention
High | Fix before release or in the next build.
Medium | Fix in a scheduled cycle.
Low | Fix when capacity allows.
Confirmed Working Correctly
Account | Check | Result
problem_user | Login successful | Pass
problem_user | Cart badge decreases correctly when items removed from Cart page | Pass
problem_user | 'Continue Shopping' button works correctly | Pass
problem_user | 'Cancel' button on Checkout Information page works correctly | Pass
problem_user | 'About' menu option opens the correct page | Pass
problem_user | 'All Items' menu option returns to Inventory page | Pass
problem_user | Cart contents retained after refreshing Cart page | Pass
problem_user | Browser Back and Forward buttons work correctly after adding items | Pass
problem_user | Cart badge updates correctly for products that can be added | Pass
problem_user | Items can be removed from the Cart page | Pass
problem_user | Cart can be opened with zero items | Pass
problem_user | Refresh works correctly | Pass
problem_user | Logout works correctly | Pass
error_user | Product names display correctly | Pass
error_user | Product prices display correctly | Pass
error_user | Product images on Inventory page are clickable | Pass
error_user | Cart badge updates correctly for items that can be added | Pass
error_user | Logout works correctly | Pass
error_user | Browser Back button works correctly | Pass
error_user | Page refresh works correctly | Pass
error_user | Cart can be opened with zero items | Pass
error_user | Items can be removed successfully from the Cart page | Pass

## Bug Report
SauceDemo Manual Test Defect Report
Total Bugs | 10
Closed Bugs | 0
Fixed Bugs | 0
In Progress | 0
Open Bugs | 10
Reopened Bugs | 0
Defect ID | Original IDs | Summary | Page / Area | Affected Accounts | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Evidence | Notes / To verify
DEF-001 | BUG-001 | All products show the same incorrect image | Inventory | problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user (password: secret_sauce) 3. Look at the product images on the Inventory page | Each product shows its own image | All 6 products show the same dog image | Medium | High | New/Open |  | Cosmetic, but the first thing every user sees.
DEF-002 | BUG-002 | Product detail page shows another product's information | Product detail | problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user (password: secret_sauce) 3. Click a product name or image 4. Compare the detail page name, description and price with the product clicked | Detail page matches the product clicked (name, description, price) | Detail page shows a different product's information | High | High | New/Open |  | Record which product opened which, e.g. clicked Product 1 → opened Product ? [FILL IN]
DEF-003 | BUG-003 | Product 4 detail page shows 'ITEM NOT FOUND' and invalid price | Product detail | problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user (password: secret_sauce) 3. Click Product 4 (name: [FILL IN]) 4. Observe the detail page | Product 4's correct name, description and price load | Page shows "ITEM NOT FOUND" and price "$√-1" | High | High | New/Open |  | Confirm Product 4's name so devs can find it.
DEF-004 | BUG-004, BUG-010 | Sorting is broken for every sort option | Inventory (sort dropdown) | problem_user, error_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user, then repeat as error_user (password: secret_sauce) 3. Open the sort dropdown 4. Select each option in turn (A–Z, Z–A, price low–high, price high–low) | Products reorder by the selected criterion | Error "Sorting is broken! This error has been reported to Backtrace." and no reordering | High | Medium | New/Open |  | Same behaviour on both accounts.
DEF-005 | BUG-005, BUG-011 | Only 3 of 6 products can be added to cart | Inventory | problem_user, error_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user, then repeat as error_user (password: secret_sauce) 3. Click 'Add to cart' on each of the 6 products 4. Check the cart badge and each button | All 6 products add to cart; badge shows 6 | problem_user: only Products 1, 2, 5 add (3, 4, 6 do not). error_user: only 3 add; the other 3 stay on 'Add to cart' | Critical | High | New/Open |  | List which 3 products fail for error_user [FILL IN]. Half the catalog can't be bought.
DEF-006 | BUG-006, BUG-013 | Product images missing on Cart page | Cart | problem_user, error_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user, then repeat as error_user (password: secret_sauce) 3. Add a product that can be added 4. Click the cart icon | Cart shows image, name, description and price | Product image is not displayed | Medium | Low | New/Open
DEF-007 | BUG-007 | Checkout: Last Name field does not accept input | Checkout: Your Information | problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user (password: secret_sauce) 3. Add a product that can be added 4. Open Cart → click Checkout 5. Click the Last Name field and type a name | Last Name accepts input; checkout can continue | Field does not accept input; checkout cannot be completed | Critical | High | New/Open |  | VERIFY exact behaviour: does typing land in another field (e.g. First Name) or get rejected? Describe precisely. error_user checkout not tested.
DEF-008 | BUG-008, BUG-015 | 'Reset App State' menu option is not clickable | Burger menu | problem_user, error_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user, then repeat as error_user (password: secret_sauce) 3. Add an item 4. Open the burger menu 5. Click 'Reset App State' | App state resets (cart emptied, buttons revert) | Option does not respond to clicks | Low | Low | New/Open
DEF-009 | BUG-009, BUG-014 | 'Remove' button does not remove the item outside the Cart page | Product detail (problem_user); Inventory (error_user) | problem_user, error_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user, then repeat as error_user (password: secret_sauce) 3. Add a product that can be added 4. Click 'Remove' (detail page for problem_user, Inventory for error_user) 5. Open Cart and remove it there | Item is removed and button reverts to 'Add to cart' | No effect; item can only be removed from the Cart page | Medium | Medium | New/Open |  | Rated Medium on both accounts because a workaround exists (Cart page). Check whether each account also fails on the other page.
DEF-010 | BUG-012 | Product description fails to render | Inventory | error_user | 1. Open https://www.saucedemo.com 2. Log in as error_user (password: secret_sauce) 3. Read the product descriptions on the Inventory page | Each product shows its own description | Placeholder text: "A description should be here, but it failed to render! This error has been reported to Backtrace." | Medium | Medium | New/Open |  | List which products are affected [FILL IN].

## Summary
Defect Summary
Severity | Unique defects
Critical | 2
High | 3
Medium | 4
Low | 1
Total | 10
Priority | Unique defects
Urgency | 0
High | 5
Medium | 3
Low | 2
Total | 10